## Slide 1: CBETA Magnet Production
and non-scaling FFA proliferation

## Slide 2: What is CBETA?
It’s a non-scaling (linear field) FFA
It’s an energy-recovery linac (ERL)
It’s both at the same time
  EMMA was an FFA ring with ERL injector (ALICE)
  CBETA is a racetrack FFA with linac inside it
Dejan has probably explained this already

## Slide 3: Timeline
Summer 2017: ATF-FFA girder with beam at BNL, 3.8x momentum range (my FFA’17 talk)
  12 permanent magnets
May 2018: CBETA girder beam test at Cornell
Now: CBETA magnet+girder production ~50% complete, estimate finish end of November
  100+  216 permanent magnets
March 2019: CBETA commissioning starts

## Slide 4
CBETA first splitter line and first FFA girder at Cornell
FFA girder

## Slide 5
CBETA first FFA girder at BNL
Half-length magnet for matching

## Slide 6
CBETA first FFA girder under construction at BNL

## Slide 7
CBETA permanent magnet containing tuning wire insert

## Slide 8: EMMA/ATF/CBETA Comparison
Parameter | EMMA | ATF-FFA | CBETA girder | CBETA (future) | Units
Energy range | 10.0–20.0 | 18.0–70.5 | 37.5–58.5 | 41.5–149.5 | MeV k.e.
Momentum ratio | 1.953 | 3.837 | 1.553 | 3.572 | ×
Radius of curvature | 2.63720 | 2.01367 | 5.08787 | 5.08787–∞ | m
Effective avg. dipole | 0.02594 | 0.11761 | (0.09834) | 0.09834 | T
Total angle | 360 | 40 | 20 | 280 | degrees
Operation mode | Storage ring | Transfer line | Transfer line | ERL | 
Acceleration? | Yes (lots!) | None | None | Yes (linac) | 
Lattice | Doublet | Close to FODO | Doublet | Doublet | 
Cell length | 0.394524 | 0.234301 | 0.444 | 0.444 | m
Cells per turn | 42 | 54 (extrapolated) | 72 (extrapolated) | 107.5 (racetrack) | 
Length built | 16.57 | 1.40581 | 1.776 | 47.73 | m

## Slide 9: Cell Tunes × 3
NB: ATF-FFA’s data fit is on matrix elements not tunes (graphs on bottom row)
EMMA
ATF-FFA
CBETA girder test
data
model

## Slide 10: Magnet Types and Parameters
QF
BD
QD
BDT2
BDT1
Magnet | Dipole (T) | Quad (T/m) | Good field radius (mm) | Aperture radius (mm) | Max field (T) (good region) | Max field (T) (aperture)
QF | 0 | -11.5624 | 25 | 43.1 | 0.2891 | 0.4983
BD | -0.3081 | 11.1475 | 25 | 40.1 | 0.5868 | 0.7551
BDT2 | -0.2543 | 11.1475 | 25 | 44.938 | 0.5330 | 0.7552
BDT1 | -0.1002 | 11.1475 | 25 | 49.085 | 0.3789 | 0.6474
QD | 0 | 11.1434 | 25 | 40.1 | 0.2786 | 0.4469

## Slide 11: Layout and Magnet Counts
Permanent magnet total: 216
QF: 107
BD: 32
BDT2: 20
BDT1: 28
QD: 27
QFH: 1 (half length)
BDH: 1

## Slide 12: Production and Testing Flow
AllStar
PM wedges
KYMA
assembly
1
3
2
4
BNL
tuning
5
Accept
Helmholtz testing at AllStar, 100% of blocks but not temperature controlled
Temperature-controlled Helmholtz test of ~15% sample at BNL for verification
Remainder of blocks shipped directly to KYMA, who also re-test ~10% sample
Rotating coil measurement of bare magnet at BNL
Rotating coil measurement of tuned magnet at BNL

## Slide 13
48% complete
104 / 214 magnets (110 remaining)

## Slide 14
BDT1 2 / 28 magnets (26 remaining)
BDT2 2 / 20 magnets (18 remaining)
BD 9 / 32 magnets (23 remaining)
QD 26 / 27 magnets (1 remaining)
QF 65 / 107 magnets (42 remaining)

## Slide 15: Projections
Method | Rotating Coil Measurements per Week | Magnets Tuned per Week | Projected Finish Date | Speed-up Required to Finish Nov-30
Magnets rate since main production start |  | 9.92 | Nov-26 | 4 calendar days spare
Rotating coil rate last 3 weeks plus model | 30.3 | 10.76 | Nov-20 | 10 calendar days spare
Rotating coil rate since start | 26.9 | 9.46 | Nov-30 | 0.5%
Required to hit deadline | 27.0 | 9.51 | Nov-30 | 0%

## Slide 16
Permanent magnets shipped from KYMA

## Slide 17
Rotating coil magnet measurement at BNL

## Slide 18
Rotating coil magnet measurement at BNL

## Slide 19
Wire tuning packs for CBETA magnets

## Slide 20: Tuned Magnets Criteria
Midplane error (G) | Units FOM | CBETA FOM | Quad error at x=0 (rel.)
≤ 1.5 | ≤ 10 | ≤ 0.375 | ≤ 0.05% (Q)
Unit = 10-4 of main pole
FOM is sqrt(sum of all (multipoles in units)2)
  CBETA FOM is weighted version based on tracking
Midplane error generally hardest to achieve
  May go in and out of spec slightly (~0.5G) due to chiller cycle

## Slide 21: Example Harmonics (QF 2566)
-1.53782 | 0
8.20E-64 | 1.87E-65
10000 | 1.26E-12
-0.2922 | -0.58294
-0.07957 | 0.201785
0.572878 | -0.88759
-0.44538 | -0.60878
0.015517 | -0.12825
0.064316 | -0.07939
0.038948 | 0.018125
0.051198 | 0.022414
0.037202 | -0.01268
-0.01854 | -0.01006
-0.01217 | -0.07378
-0.09591 | -0.03929
-0.00478 | 0.020399
-0.01032 | -0.01952
0.007539 | 0.007748
0.068582 | 0.001058
-0.00071 | 0.001648
-0.00187 | -0.00071
Displaced magnet by DX (m) | -0.0002
DY (m) | -0.00156
Rotated A/C by (rad) | 0.041074
(deg) | 2.353343
Reference radius (m) | 0.025
Normal
Skew
Integrated strength (T/m.m)
Dipole
Quad
Sext
Oct
etc.

## Slide 22: Water Cooling Stability

## Slide 23
BD
QF
QD
BDT1
BDT2
Reversed block
Mislabelled block
Reversed block
Mislabelled block

## Slide 24: Rejects/Repaired
BD 2305
Harmonics simulation w/swap
QF 2509
Harmonics simulation w/swap
QD 2427
Harmonics sim. w/type change
QF 2572
Harmonics sim. w/type change

## Slide 25: Reversed Block in QF 2509

## Slide 26
BD
QF
QD
Only tuned magnets shown (4 “rejects” also removed)
BDT1
BDT2

## Slide 27
BD
QF
QD
Only tuned magnets shown (4 “rejects” also removed)
BDT1
BDT2

## Slide 28
CBETA windowframe correctors at BNL

## Slide 29
CBETA girder production at BNL

## Slide 30: Other Problems/Lessons Learned
@BNL
  Warehouse roof leaks, hence tent in photo
  Gaps when reassembling magnets from halves
@AllStar
  Some blocks went rusty (not passivated?), had them re-made
  One type magnetisation angle was out-of-spec, had them re-made
@KYMA
  Couple of blocks inserted backwards
  One glue failure, exploding magnet, repaired
Team effort
  Block width with chamfer was not communicated clearly to AllStar, meaning blocks slightly larger than needed, had trouble fitting
  Chinese sign convention for magnetisation was opposite, had to invert blocks

## Slide 31: Backup

## Slide 32: Helmholtz Measurements
Example: AllStar data for wedge types P1 through P16 (BD magnet)
Angle errors Strength variation

## Slide 33: Magnetisation Angle Distributions
Requested that factory re-make types P15 and P16 to reduce systematic error.
These are the smallest blocks, so not critical, but re-make will improve quality of untuned magnets.
General request was for 1 degree RMS error, but can cope with some above and some below as we have here (see next slide)

## Slide 34: Magnet Error Model
Both the strength and angle error distribution can be put back into the field simulation
Example: BD magnet using AllStar’s data set.
1000 magnets were generated, some with position errors. Histogram is binned by the “units FOM”.
Green = easy to tune
Red = possible problems
Based on first girder experience.