# Cbeta Technical Issues 2016-Jan-21

Unknowns to be investigated and resolved ASAP after this meeting.  Generally these are on the critical path or lead to a decision point.  This document is just for our own reference.

# Upcoming Itinerary

TRIP TO SBIR COMPANY (EEC, Pennsylvania)  In February?  (Stephen, Holger, George, Bruce, Dejan, Karl…)  Talk via e-mail with EEC (Dejan?)

NEXT COLLABORATION MEETING (Venue: Cornell)  Date?  Some time in March.  Georg to provide free dates, Stephen to set up Doodle Poll.

# Decision: Corrugated Pipe or not?

The “Brooks” lattice varied the pipe and magnet bore radii to reduce the outer magnet radii to ~6cm, Chris’s lattice with an equal-size pipe, which is simpler, required ~8cm radius magnets.  This is all assuming Halbach magnets (see next section).  Worry is that corrector, particularly the quad, could become difficult, power-hungry and lose field into adjacent magnets due to the larger aperture.  Bruce would prefer un-corrugated pipe if at all possible.

## Actions

- (2 weeks) Nick Tsoupas to find if a 2% quad corrector can be designed to go around Chris’s larger magnet

  - Should check power/heat requirements

  - Is water cooling required? (assume both dipoles + quad)

- (2 weeks) Chris (and Dejan) should try and make his tunes further away from 1/3 (more like the Brooks cell)

  - Then, if going ahead, Stephen can scan for resonances

- (If constant radius pipe not easily possible) Wakefield calculations for feasibility of corrugated pipe, check for trapped modes

# Linac Energy Assumption

61MeV already is conservative and low risk assumption.

Every cavity has been tested to 14MeV.  So already have 5*14=70MeV in hand.

# Decision: Can an iron-poled quad be used?

Although this will ultimately depend on the results from prototyping, the lattice has changed since Holger’s original design with the too-small aperture.  The recent lattices were optimised to make the Halbach magnets easier, but they may also make the iron poled magnet easier because the gradients have come down.

Suggestion from Georg+Bruce: see what can be done without the temperature control.

## Actions

- (2 weeks) Holger find what pole-tip radius is possible in an iron quad with the new QF gradient.  We then compare that with possible vacuum pipes.

- (Scott) Reoptimise lattice for iron magnets.

- May need to find out if an oval pipe helps.

- May need to reconsider 12+5=17mm centroid-to-magnet distance.

# Check: Linac Final Placement vs. Required Space for FFAG in Hall

FFAG arcs options have R=5m or R=5.25m.  Splitter length is undecided, can we verify the hall can fit the largest version currently considered?  Knocking the wall down is not too expensive/dangerous?  Is there a reassuring drawing of this?

## Actions

- (Bruce, 1 week) Find out margin on South wall and what value of R is possible

- (Bruce et al., 1 week) Show L0E layout drawing with appropriate space

# Decision: What sort of extraction?

Should it be necessary for early-stage commissioning (e.g. 1-pass ERL), or be able to be added later?  Answer (from people including Georg): no.  Early stage machine has no extraction of either type and a pi/2 delay in the splitter.

Options: Could extract from splitter (potentially 311MeV), or from FFAG?  Consider adding simple FODO electromagnetic ring from splitter for highest energy (Georg approves of this in principle).

## Actions (later because not in initial design)

- Estimate cost of the FODO line

- Try to design FFAG extraction from straight section where the magnets are smaller.  Open midplane may be possible for the smaller QFS and BDS magnets

# Commissioning Sequence

See Michiko’s talk?  Instrumentation relies on what needs to be measured in the machine and during commissioning.

Scott has some responsibility (not present).  Too early to decide now.

# Magnet Types Inventory

(First draft in Stephen’s talk)

Chris Mayes provides information about splitter to Karl Smolensky.

For FFAG loop, after corrugated pipe desicision, Chris/Stephen provide lattice  Stephen provides 2D design  Nick Tsoupas does OPERA-3D modelling and produces fieldmaps.  Probably should use 5-type scheme (QF, BD, [BDT], QFS, BDS).

Other types of magnet – Bruce has conventional dipoles and correctors for injection/dump?  No quads in Linac.

# Magnet Construction, Measurement and Testing Process

E.g. magnet construction company does most of the measurements but (Wolfram and Georg agree) test all magnets, if possible, at least by rotating coil in SMD at BNL.

Bruce: should we re-test magnets when split and unsplit from halves?  This should be in the spec to the company.

Should we pay Animesh or other SMD staff for this work?  Or do we use the C-AD SMD effort pool?

Bruce: no magnet measurements at Cornell.  Cornell will align them onto the real machine and survey them (also supervise production rate).

# Assembly Method for FFAG Magnets, Vacuum Chamber, Correctors

Karl and Yulin main people, requiring input from magnet design (see above).  Xiang Hong is in charge of installation at Cornell.  Depends on other decisions for now.

## Actions

- (Stephen, Holger, Nick, 2 weeks) Find out if there is as special plane to split the magnets which minimises forces between the halves.

# Additional Simulations (error studies, to support commissioning, etc.)

- Correctors (both dipole + quad) every magnet vs. every 2 magnets

  - (Chris, Chuyu, Francois, 4 weeks) Does correction work with correctors only around QF magnets?

  - Ultimately use fieldmaps from Nick Tsoupas

- (Feb 4th, 5th, David Sagan, Chris Mayes) Organise BMAD workshop at BNL

- Ongoing: get graduate students from Stony Brooks, Cornell for simulations

- Once final lattice is set:

  - Put multipole errors from Halbach magnets back into simulation (Stephen)

  - Include realistic roll errors: do we need skew quads?

  - Lots of collective effects simulations

  - Calculate impedance budget, requires mechanical design of beam pipe, instrumentation etc.

  - Vacuum quality simulation (Yulin…), requires beam pipe shape

# Information Exchange (Actions)

- Stephen to send Yulin Li the (x,y,z) coordinates of the magnet bore cylinders and beam clearance “keep-clear” cylinders of a whole girder (assumed to be 4 cells)

  - Chris could do the same for his cell

- Cornell to give Michiko beam requirements (intensity, emittance, bunch length etc.)

- NB: in future, should come up with a proper configuration control system for the design

  - This should include a person’s name against each topic and ideally also a link to the data file

  - Find exchange format for 3D magnet models (Yulin Li, Tim O’Connell) e.g. STP file

  - Needs further discussion

# Other stuff to proceed with immediately (Actions)

- Nick Tsoupas’ corrector superposition experiment at BNL

  - Can also build a corrector windowframe at BNL without needing PM pieces

- Investigate adding path length adjustment dogleg to the splitter and quantify the adjustment that can be made by just changing the orbit within the pipe (Chris, Dejan)