## Slide 1: CBETA Magnets 1302, 1303
First girder BD2, BD3

## Slide 2: Last Week
Tue: BD2 wire pack iterations, 80mil shims seemed on edge, so tried iteration of 105mil
Wed: BD3, already had 1st iter wire set, good result, tried 2nd iteration no real improvement
  Meanwhile, add water fittings to BD4
Thu-Sun: Thanksgiving
Mon: BD3 final survey, measurement
  Slight delay as John C. hit a deer with his truck

## Slide 3: 1302 / FG BD2 History
Run # | Max error on midplane (Gauss) | Quad strength error | Multipole sqrt(sumsq) (units) | CBETA FOM | Notes
3 | ? | Wrong temperature | 12.00 | 0.387 | Iteration 2 but at wrong temp.
4 | 28.34 | -0.921% | 10.78 | 0.371 | Remeasured 85F
5 | 21.63 | +0.973% | 108.94 | 3.329 | Software error
7 | 11.94 | -0.074% | 16.67 | 0.555 | Error fixed, 80mil on edge of range
8 | 3.49 | -0.196% | 19.28 | 0.539 | 105mil iteration

## Slide 4: BD2 Midplane Field Error
Chart: 
Chart: 
Chart: 

## Slide 5: BD2 Comments
The software error in PM_Correct has been fixed
Evidence that some first girder BD magnets will require 105mil shims
  This was an option considered before but BD1 and BD3 were rebuilt because even 105mil shims couldn’t fix them originally!
We’ll come back to BD2 later to tune more precisely

## Slide 6: 1303 / FG BD3 History
Run # | Max error on midplane (Gauss) | Quad strength error | Multipole sqrt(sumsq) (units) | CBETA FOM | Notes
12 | 35.28 | -0.324% | 68.15 | 2.185 | Bare (rebuilt) magnet at 85F
13 | 1.76 | +0.048% | 5.98 | 0.159 | Wire iteration 1
14 | 2.09 | +0.034% | 9.50 | 0.275 | Wire iteration 2
15 | 2.08 | +0.030% | 9.05 | 0.265 | Remeasured with survey on Monday

## Slide 7: BD3 Midplane Field Error
Chart: 
Chart: 
Chart: 

## Slide 8: BD3 Comments
Very good 1st iteration, but no progress on 2nd iteration
Magnet was borderline acceptable on both iterations, better than 10^-3 on all measures
Looked at code for errors on 2nd iteration, haven’t found anything
Possibly 105mil shims might help here too, as lots of maxed-out wires, little to adjust

## Slide 9: Harmonics BD2, BD3
1.36046 | 0
-11052.1 | 5.61E-13
10000 | 1.32E-13
-4.40731 | -1.97829
-5.93374 | 2.944767
2.97768 | 2.993214
0.235969 | 0.331699
-1.30166 | -1.00971
-0.24904 | 0.675352
-0.50094 | 0.221363
-0.61446 | -0.06241
-0.41096 | -0.14886
-0.61571 | -0.13387
-0.1393 | -0.11245
0.3327 | -0.12456
0.485923 | 0.009312
0.135705 | 0.23037
-0.09568 | -0.07306
0.076317 | -0.02739
0.109141 | -0.01767
0.025043 | 0.025702
Displaced magnet by DX (m) | -0.00128
DY (m) | -0.00174
Rotated A/C by (rad) | 0.075818
(deg) | 4.344046
1.357332 | 0
-11077.6 | 6.82E-13
10000 | 5.75E-14
-6.91808 | -5.35137
13.77272 | -6.46008
2.287861 | 5.568673
0.582745 | 3.78755
-2.40745 | -0.56327
0.637382 | 0.894697
1.294063 | 0.228752
1.027118 | -0.6926
0.566225 | 0.318002
-0.3854 | 0.752875
-0.66622 | 0.63118
-0.21276 | -0.49362
0.205531 | 0.00076
0.138472 | 0.164184
-0.13624 | -0.06352
0.083461 | -0.02249
0.136325 | -0.0352
0.040854 | 2.59E-05
Displaced magnet by DX (m) | -0.00126
DY (m) | -0.00151
Rotated A/C by (rad) | 0.075214
(deg) | 4.309462

## Slide 10: All FG Magnets Status
Magnet name | Max error on midplane (Gauss) | Quad strength error | Multipole sqrt(sumsq) (units) | CBETA FOM | Notes
BD1 (rb) | 8.06 | +0.058% | 23.55 | 0.773 | New iter 1
BD2 | 3.49 | -0.196% | 19.28 | 0.539 | 105mil wire
BD3 (rb) | 2.08 | +0.030% | 9.05 | 0.265 | New iter 2
BD4 | ? | Wrong temp | 9.13 | 0.247 | Old iter 2
QF1 | ? | Wrong temp | 3.38 | 0.114 | Old iter 1
QF2 | ? | Wrong goal | 7.30 | 0.149 | Old iter 1
QF3 (ra) | ? | Wrong goal | 4.78 | 0.099 | Old iter 2
QF4 (ra) | ? | Wrong temp | 21.25 | 0.273 | Old iter 1
(rb) = rebuilt, (ra) = reassembled from halves

## Slide 11: Next Week
Tue: BD4 measurement, first 85F iteration
Wed: BD4 E4E coil roll check and survey
Thu: QF1
Fri: QF2?
Mon: QF3?
  Need to do HMAC-requested extra iterations on BD1 and BD2 later