## Rate
Date |  |  |  |  | Number of rotating coil measurements
Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Sum | Notes
2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 |  |  |  |  | 2 | 2 | Batch only arrived Friday p.m.
2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 3 | 3 | Holiday | 4 | 0 | 10 | John C. on vacation this week, only Toby. Also PC software issue on Friday
2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 4 | 3 | 5 | 5 | 4 | 21
Formulas:
Tuesday = [Monday]+1
Tuesday = [Tuesday, row above]+7
Wednesday = [Tuesday]+1
Monday = [Monday, row above]+7

## Redos
Magnet type | Total magnets | Percent redos | Redos | Number accepted (2000 series) |  | Remaining | Redos
QF | 107 | 10% | 10.7 | 10 | 9.346% | 97 | 9.7
QD | 27 | 10% | 2.7 | 5 | 18.52% | 22 | 2.2
BD | 30 | 66.67% | 20 | 7 | 23.33% | 23 | 15.3333
BDT1 | 28 | 66.67% | 18.6667 | 0 | 0% | 28 | 18.6667
BDT2 | 22 | 66.67% | 14.6667 | 0 | 0% | 22 | 14.6667
Total | 214 | 31.18% | 66.7333 | 22 | 10.28% | 192 | 60.5667 | 31.55%

## Model
8.21 | magnets per week | 2 | coil benches | 31.55% | iteration re-dos | 5 | working days per week
Rotating coil measurements
8.21 | first measurements
10.7999 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
21.0099 | total coil measurements per week
4.202 | coil measurements per day
2.101 | coil measurements per bench per day
Magnet surveys at bench
8.21 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
10.21 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
10.7999 | per week
2.16 | per day
Schedule
214 | Total magnets
22 | Magnets done
192 | Magnets remaining
23.3861 | weeks to complete (no contingency)
Current date | 2018-07-13
End date | 2018-12-23 16:52

## Example model
8 | magnets per week | 2 | coil benches | 25% | iteration re-dos | 5 | working days per week
Rotating coil measurements
8 | first measurements
10 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
20 | total coil measurements per week
4 | coil measurements per day
2 | coil measurements per bench per day
Magnet surveys at bench
8 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
10 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
10 | per week
2 | per day
Schedule
216 | Total magnets
14 | Magnets done
202 | Magnets remaining
25.25 | weeks to complete (no contingency)
Start date | 2018-07-02
End date | 2018-12-25 18:00

## Example week
|  | Coil measurements | [8 empty] | Shim packs |  | Survey
|  | Initial measurement |  | First iterations |  | Extra iterations |  | E4E calibration |  | Per day |  | Per day |  | Per day
|  | John | Toby | John | Toby | John | Toby | John | Toby |  | Henry, Toby, others |  | Survey group
Monday | AM | 1 | 1
| PM | 1 | 1 | [6 empty] | 4 | 1 | 1 |  | 0
Tuesday | AM | 1 | 1 | [7 empty] | 1
| PM | 1 | 1 | [6 empty] | 4 | 2 | 3 |  | 0
Wednesday | AM |  |  | 1 | 1 | [5 empty] | 2 |  | 2
| PM |  |  | 1 | 1 |  |  |  |  | 4 | 2 | 4 | 2 | 4
Thursday | AM |  |  | 1 | 1 | [5 empty] | 1 |  | 1
| PM |  |  | 1 | 1 |  |  |  |  | 4 | 1 | 2 | 1 | 2
Friday | AM |  |  |  |  | 1 | 1 | [5 empty] | 2
| PM | [6 empty] | 1 | 1 | 4 |  | 0 | 2 | 4
[9 empty] | 20 |  | 10 |  | 10

## Pessimistic model
7 | magnets per week | 2 | coil benches | 60% | iteration re-dos | 5 | working days per week
Rotating coil measurements
7 | first measurements
11.2 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
20.2 | total coil measurements per week
4.04 | coil measurements per day
2.02 | coil measurements per bench per day
Magnet surveys at bench
7 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
9 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
11.2 | per week
2.24 | per day
Schedule
216 | Total magnets
14 | Magnets done
202 | Magnets remaining
28.8571 | weeks to complete (no contingency)
30% | Contingency because they get distracted by other projects
37.5143 | weeks to complete (incl. contingency)
Start date | 2018-07-02
End date | 2019-03-21 14:24

## Pessimistic fixed
10.8 | magnets per week | 2 | coil benches | 60% | iteration re-dos | 5 | working days per week
Rotating coil measurements
10.8 | first measurements
17.28 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
30.08 | total coil measurements per week
6.016 | coil measurements per day
3.008 | coil measurements per bench per day
Magnet surveys at bench
10.8 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
12.8 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
17.28 | per week
3.456 | per day
Schedule
216 | Total magnets
14 | Magnets done
202 | Magnets remaining
18.7037 | weeks to complete (no contingency)
30% | Contingency because they get distracted by other projects
24.3148 | weeks to complete (incl. contingency)
Start date | 2018-07-02
End date | 2018-12-19 04:53