## Slide 1: CBETA Production Magnets
QD 2414-20, 2422, 2423
QF 2518-26, 2529, 2530, 2534-37

## Slide 4: Projections
Method | Rotating Coil Measurements per Week | Magnets Tuned per Week | Projected Finish Date | Speed-up Required to Finish Nov-30
Magnets rate since main production start |  | 11.01 | Nov-15 | 15 calendar days spare
Rotating coil rate last 3 weeks plus production model | 29.3 | 10.39 (includes assumption for more iterations for future BD, coil slips etc.) | Nov-21 | 9 calendar days spare
Required to hit deadline (using model) | 27.2 | 9.57 | Nov-30 | 0%

## Slide 5
BD
QF
QD
All magnets are shown, those under consideration this week are under light blue bars
BDT1
BDT2

## Slide 6
BD
QF
QD
All magnets are shown, those under consideration this week are under light blue bars
BDT1
BDT2

## Slide 7
BD
QF
QD
All magnets are shown, those under consideration this week are under light blue bars
If magnets are not tuned yet, the untuned value is shown
BDT1
BDT2

## Slide 8
BD
QF
QD
BDT1
BDT2
All magnets are shown, those under consideration this week are under light blue bars
If magnets are not tuned yet, the untuned value is shown

## Slide 9: Tuned Magnets Criteria
Midplane error (G) | Units FOM | CBETA FOM | Quad error at x=0 (rel.)
≤ 1.5 | ≤ 10 | ≤ 0.375 | ≤ 0.05% (Q)
For full data see spreadsheets “initialmagnets” “finalmagnets”
Midplane error generally hardest to achieve
  May go in and out of spec slightly (~0.5G) due to chiller cycle
Achieving all the above triggers “quick accept”

## Slide 10: Status
Tuning of 2nd crate containing QFs and all remaining QD magnets nearly done
3rd crate to arrive this week, containing only QFs
Separate delivery of 3 BD magnets coming at some point to complete an arc girder
4th crate also only QF magnets
  >90 QFs manufactured at KYMA