## Rate
Date | [5 empty] | Number of rotating coil measurements
Monday | Tuesday | Wednesday | Thursday | Friday |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sum | Notes
2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | [5 empty] | 2 |  | 2 | Batch only arrived Friday p.m.
2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 |  | 3 | 3 | Holiday | 4 | 0 |  | 10 | John C. on vacation this week, only Toby. Also PC software issue on Friday
2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 |  | 4 | 3 | 5 | 5 | 4 |  | 21
2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 |  | 5 | 7 | 4 | 4 | 2 |  | 22 | John C. out on Friday
2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 |  | 5 | 2 | 5 | 6 | 5 |  | 23 | Most of survey group out this week (just Chenghao)
2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 |  | 7 | 5 | 7 | 5 | 6 |  | 30
2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 |  | 7 | 8 | 7 | 7 | 6 |  | 35
2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 |  | 8 | 7 | 3 | 10 | 9 |  | 37 | SJB out Weds, Thurs a.m.
2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 |  | 6 | 9 | 8 | 9 | 0 |  | 32 | John C. out on Friday (probably Toby too)
2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 |  | 6 | 7 | 6 | 8 | 4 |  | 31 | Ming out this week, survey group busy
2018-09-03 | 2018-09-04 | 2018-09-05 | 2018-09-06 | 2018-09-07 |  | Holiday | 4 | 8 | 10 | 6 |  | 28 | John C. out on Tuesday
2018-09-10 | 2018-09-11 | 2018-09-12 | 2018-09-13 | 2018-09-14 |  | 7 | 7 | 6 | 6 | 7 |  | 33
2018-09-17 | 2018-09-18 | 2018-09-19 | 2018-09-20 | 2018-09-21 |  | 3 | 6 | 5 | 2 | 2 |  | 18 | started to wait for BD crate delivery
2018-09-24 | 2018-09-25 | 2018-09-26 | 2018-09-27 | 2018-09-28 |  | 3 | 2 | 2 | 5 | 6 |  | 18 | John C.'s coil (#76) electronics broken Weds-Fri (also sort of waiting for BD delivery)
2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 |  | 7 | 7 | 9 | 8 | 7 |  | 38
2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 |  | Holiday | 6 | 5 | 2 | 2 |  | 15 | John C.'s coil (#76) electronics broken last half of the week
2018-10-15 | 2018-10-16 | 2018-10-17 | 2018-10-18 | 2018-10-19 |  | 4 | 4 | 3 | 1 | 2 |  | 14 | John C.'s coil (#76) electronics still broken
2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 |  | 4 | 7 | 8 | 12 | 5 |  | 36 | John C. on vacation and coil #76 broken
2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 |  | 4 | 7 | 9 | 8 | 12 | 4 | 44 | Chiller broke, then replaced, coil #76 fixed mid-week before John C. returned
2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 |  | 10 | 11 | 12 | 12 | 6 |  | 51
2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 |  | Holiday | 6 | 1 |  |  |  | 7
[5 empty] | Total | 93 | 118 | 113 | 124 | 93 | 4 | 545
Formulas:
Tuesday = [Monday]+1
Tuesday = [Tuesday, row above]+7
Wednesday = [Tuesday]+1
Monday = [Monday, row above]+7

## Redos
Magnet type | Total magnets | Percent redos | Redos | Number accepted (2000 series) |  | Remaining | Redos
QF | 107 | 55% | 58.85 | 97 | 90.65% | 10 | 5.5
QD | 27 | 32% | 8.64 | 27 | 100% | 0 | 0
BD | 32 | 66.67% | 21.3333 | 30 | 93.75% | 2 | 1.3333
BDT1 | 28 | 50% | 14 | 28 | 100% | 0 | 0
BDT2 | 20 | 50% | 10 | 2 | 10% | 18 | 9
Total | 214 | 52.72% | 112.8233 | 184 | 85.98% | 30 | 15.8333 | 52.78%

## Model (simple)
10.1269 | magnets per week |  | 2 | coil benches | 52.78% | iteration re-dos | 5 | working days per week
Rotating coil measurements |  |  |  |  | 10 | weeks between unrecoverable calibration slips (on any given coil)
10.1269 | first measurements
5.3447 | extra iterations
10.1269 | final iterations
2 | additional E4E measurements per week (one per coil bench)
0.81269 | Extra measurements due to calibration slips
28.4111 | total coil measurements per week
5.6822 | coil measurements per day
2.8411 | coil measurements per bench per day
Magnet surveys at bench
10.1269 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
0.81269 | Extra surveys due to calibration slips
12.9395 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
10.1269 | per week
2.0254 | per day
Schedule
214 | Total magnets
184 | Magnets done
30 | Magnets remaining
2.9624 | weeks to complete (no contingency)
Current date | 2018-11-05
End date | 2018-11-25 17:41
Goal | 2018-11-30 | -17.05% | speed-up needed

## Model
11.24 | magnets per week |  | 2 | coil benches | 52.78% | iteration re-dos | 5 | working days per week
Rotating coil measurements |  |  |  |  | 10 | weeks between unrecoverable calibration slips (on any given coil)
11.24 | first measurements
5.9322 | extra iterations
11.24 | final iterations
2 | additional E4E measurements per week (one per coil bench)
0.924 | Extra measurements due to calibration slips
31.3362 | total coil measurements per week
6.2672 | coil measurements per day
3.1336 | coil measurements per bench per day
Magnet surveys at bench
11.24 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
0.924 | Extra surveys due to calibration slips
14.164 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
11.24 | per week
2.248 | per day
Schedule
214 | Total magnets
184 | Magnets done
30 | Magnets remaining
2.669 | weeks to complete (no contingency)
Current date | 2018-11-05
End date | 2018-11-23 16:24
Goal | 2018-11-30 | -25.27% | speed-up needed

## Example model
8 | magnets per week | 2 | coil benches | 25% | iteration re-dos | 5 | working days per week
Rotating coil measurements
8 | first measurements
10 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
20 | total coil measurements per week
4 | coil measurements per day
2 | coil measurements per bench per day
Magnet surveys at bench
8 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
10 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
10 | per week
2 | per day
Schedule
216 | Total magnets
14 | Magnets done
202 | Magnets remaining
25.25 | weeks to complete (no contingency)
Start date | 2018-07-02
End date | 2018-12-25 18:00

## Example week
|  | Coil measurements | [8 empty] | Shim packs |  | Survey
|  | Initial measurement |  | First iterations |  | Extra iterations |  | E4E calibration |  | Per day |  | Per day |  | Per day
|  | John | Toby | John | Toby | John | Toby | John | Toby |  | Henry, Toby, others |  | Survey group
Monday | AM | 1 | 1
| PM | 1 | 1 | [6 empty] | 4 | 1 | 1 |  | 0
Tuesday | AM | 1 | 1 | [7 empty] | 1
| PM | 1 | 1 | [6 empty] | 4 | 2 | 3 |  | 0
Wednesday | AM |  |  | 1 | 1 | [5 empty] | 2 |  | 2
| PM |  |  | 1 | 1 |  |  |  |  | 4 | 2 | 4 | 2 | 4
Thursday | AM |  |  | 1 | 1 | [5 empty] | 1 |  | 1
| PM |  |  | 1 | 1 |  |  |  |  | 4 | 1 | 2 | 1 | 2
Friday | AM |  |  |  |  | 1 | 1 | [5 empty] | 2
| PM | [6 empty] | 1 | 1 | 4 |  | 0 | 2 | 4
[9 empty] | 20 |  | 10 |  | 10

## Pessimistic model
7 | magnets per week | 2 | coil benches | 60% | iteration re-dos | 5 | working days per week
Rotating coil measurements
7 | first measurements
11.2 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
20.2 | total coil measurements per week
4.04 | coil measurements per day
2.02 | coil measurements per bench per day
Magnet surveys at bench
7 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
9 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
11.2 | per week
2.24 | per day
Schedule
216 | Total magnets
14 | Magnets done
202 | Magnets remaining
28.8571 | weeks to complete (no contingency)
30% | Contingency because they get distracted by other projects
37.5143 | weeks to complete (incl. contingency)
Start date | 2018-07-02
End date | 2019-03-21 14:24

## Pessimistic fixed
10.8 | magnets per week | 2 | coil benches | 60% | iteration re-dos | 5 | working days per week
Rotating coil measurements
10.8 | first measurements
17.28 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
30.08 | total coil measurements per week
6.016 | coil measurements per day
3.008 | coil measurements per bench per day
Magnet surveys at bench
10.8 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
12.8 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
17.28 | per week
3.456 | per day
Schedule
216 | Total magnets
14 | Magnets done
202 | Magnets remaining
18.7037 | weeks to complete (no contingency)
30% | Contingency because they get distracted by other projects
24.3148 | weeks to complete (incl. contingency)
Start date | 2018-07-02
End date | 2018-12-19 04:53